## MTO & Cap Costs (hidden)
Wolverine Creek Options
Material Quantities
Task No. | Description | Remarks | Unit | Quantity
|  |  |  | WC-A | WC-B | WC-C | WC-D | WC-D2 | WC-E | WC-E2
1 | Major Road Improvements
1.1 | Clear & grub | Medium | ha |  | 1 | 1 | 1 | 1 | 1 | 1
1.2 | Road embankment widening, 3m | Cut to fill existing shoulder. Approx 8M3 / LM. | M3 |  | 9600 | 9600 | 9600 | 9600 | 9600 | 9600
1.2 | Re-grade road sub-base | Av. 150mm dp x 5m wide | M3 |  | 900 | 900 | 900 | 900 | 900 | 900
1.3 | Gravel resurfacing, 100mm thk x 8m wide | Drill & blast, crushing, load & haul and place. | M3 |  | 960 | 960 | 960 | 960 | 960 | 960
1.4 | Bridge construction | 50', 100 ton capacity | M3 |  | 1 | 1 | 1 | 1 | 1 | 1
2 | Bulk Earthworks
2.1 | Tailings Excavation to Wolverine Creek |  | M3
2.2 | Tailings Regrading (Dozer) |  | M3 | [5 empty] | 3000000 | 3500000
2.2 | Tailings Excavation to Mill Area |  | M3
2.3 | Tailings Excavation and Replacement |  | M3 |  | 200000 |  | 200000 |  | 200000
2.4 | Waste Rock Fill (From Clinton Creek) |  | M3 |  |  | 700000 | 700000 | 340000 | 500000 | 600000
3 | Rock Drain
3.1 | Blast rock - 100 to 500 mm dia. (end dumped) | Supply, load, haul, place | EA |  | 31000 |  | 31000 |  | 31000
3.2 | Granular Filter (Crushed Rock) | Supply, load, haul, place | M3 |  | 13000 |  | 13000 |  | 13000
4 | Channel Armouring
4.1 | Channel Profiling (Excavation) | Supply, load, haul, place | M3 |  |  | 20250 | 20250 | 20250 | 20250 | 20250
4.2 | Cobbles - 25 to 100 mm dia. | Supply, load, haul, place | M3 |  |  | 2500 | 2500 | 2500 | 2500 | 2500
4.3 | Riprap - D50 = 500 mm dia. | Supply, load, haul, place | M3
4.4 | Riprap - D50 = 800 mm dia. | Supply, load, haul, place | M3 |  |  | 2900 | 2900 | 2400 | 2900 | 2900
4.5 | Granular Filter (Crushed Rock) | Supply, load, haul, place | M3 |  |  | 2400 | 2400 | 2000 | 2400 | 2400

## WC-A
|  | SHEET TITLE: |  | Wolverine Creek Option A LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
| Status Quo - Leave As Is |  |  |  | -
Subtotal |  |  |  |  | 0
| EPCM |  |  |  | 0
| Contingency (25%) |  |  |  | 0
Total Estimated Capital Costs |  |  |  |  | 0
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 0.065363
2.1 | Clear Vegetation from Existing Rock-Lined Channel | 20000 | 10 | 100 | 0.065363
Subtotal |  |  |  |  | 1.6994
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 1.6994
Equivalent Annual Operational Costs |  |  |  |  | 0.046415
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 1.6994
Note: While this is not entirely a walk-away solution, very little regular maintenance would be required for this option. Therefore site access would not need to be maintained.

## WC-B
|  | SHEET TITLE: |  | Wolverine Creek Option B LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.262
2 | Access Road Construction |  |  |  | 1.108
3 | Rock Drain |  |  |  | 6.729
4 | Water Management |  |  |  | 0.1
5 | Support Equipment |  |  |  | 0.532
6 | Support Labour |  |  |  | 1.89
7 | Asbestos Control |  |  |  | 0.805
8 | Fuel Transportation |  |  |  | 0.014
9 | Indirects |  |  |  | 6.511
Note: Cost Breakdown in Appendix 3, Option WC-B
Subtotal |  |  |  |  | 17.951
| EPCM |  |  |  | 1.7951
| Contingency (25%) |  |  |  | 4.9365
Total Estimated Capital Costs |  |  |  |  | 24.6826
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 1.2452
2.1 | Excavate Rock Drain Sediment (at Inlet) (Cost Breakdown in Appendix 3) | 361000 | 10 | 100 | 1.1798
2.2 | Clear Vegetation from Existing Rock-Lined Channel | 20000 | 10 | 100 | 0.065363
Subtotal |  |  |  |  | 2.8792
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 2.8792
Equivalent Annual Operational Costs |  |  |  |  | 0.078637
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 27.5619
Note: While this is not entirely a walk-away solution, very little regular maintenance would be required for this option. Therefore site access would not need to be maintained.

## WC-C
|  | SHEET TITLE: |  | Wolverine Creek Option C LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.781
2 | Access Road Construction |  |  |  | 1.108
3 | Cover over Tailings Pile Base |  |  |  | 5.264
4 | Channel Stabilization |  |  |  | 1.064
5 | Water Management |  |  |  | 0.082
6 | Support Equipment |  |  |  | 0.421
7 | Support Labour |  |  |  | 1.485
8 | Asbestos Control |  |  |  | 0.802
9 | Fuel Transportation |  |  |  | 0.022
10 | Indirects |  |  |  | 5.842
Note: Cost Breakdown in Appendix 3, Option WC-C
Subtotal |  |  |  |  | 16.871
| EPCM |  |  |  | 1.6871
| Contingency (25%) |  |  |  | 4.6395
Total Estimated Capital Costs |  |  |  |  | 23.1976
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 0.065363
2.1 | Clear Vegetation from Existing Rock-Lined Channel | 20000 | 10 | 100 | 0.065363
3 | Replacement |  |  |  | 0.31666
3.1 | Replace 200m of 0.1% Channel (North Lobe) (Cost Breakdown in Appendix 3) | 705000 | 45 | 100 | 0.31666
3.2 | Replace 200m of 0.1% Channel (South Lobe) (Cost Breakdown in Appendix 3) | 705000 | 12 | 100 | 1.8711
Subtotal |  |  |  |  | 3.8872
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 3.8872
Equivalent Annual Operational Costs |  |  |  |  | 0.10617
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 27.0848
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (16.2 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (16.2 km) (Cost Breakdown in Appendix 3) | 4318000 | 20 | 100 | 6.1891
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 7.2138
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 7.2138
Equivalent Annual Cost |  |  |  |  | 0.19702
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## WC-D
|  | SHEET TITLE: |  | Wolverine Creek Option D LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.968
2 | Access Road Construction |  |  |  | 1.102
3 | Rock Drain |  |  |  | 6.935
4 | Cover over Tailings Pile Base |  |  |  | 5.264
5 | Channel Stabilization |  |  |  | 1.024
6 | Water Management |  |  |  | 0.145
7 | Support Equipment |  |  |  | 0.569
8 | Support Labour |  |  |  | 2.025
9 | Asbestos Control |  |  |  | 0.843
10 | Fuel Transportation |  |  |  | 0.034
11 | Indirects |  |  |  | 10.42
Note: Cost Breakdown in Appendix 3, Option WC-D
Subtotal |  |  |  |  | 29.329
| EPCM |  |  |  | 2.9329
| Contingency (25%) |  |  |  | 8.0655
Total Estimated Capital Costs |  |  |  |  | 40.3274
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 1.2452
2.1 | Clear Vegetation from Existing Rock-Lined Channel | 20000 | 10 | 100 | 0.065363
2.2 | Excavate Rock Drain Sediment (at Inlet) (Cost Breakdown in Appendix 3) | 361000 | 10 | 100 | 1.1798
3 | Replacement |  |  |  | 0.31666
3.1 | Replace 200m of 0.1% Channel (North Lobe) (Cost Breakdown in Appendix 3) | 705000 | 45 | 100 | 0.31666
3.2 | Replace 200m of 0.1% Channel (South Lobe) (Cost Breakdown in Appendix 3) | 705000 | 12 | 100 | 1.8711
Subtotal |  |  |  |  | 5.067
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 5.067
Equivalent Annual Operational Costs |  |  |  |  | 0.13839
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 45.3944
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (16.2 km) (Cost Breakdown in Appendix 3) | 4318000 | 20 | 100 | 6.1891
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 7.2138
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 7.2138
Equivalent Annual Cost |  |  |  |  | 0.19702
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## WC-D2
|  | SHEET TITLE: |  | Wolverine Creek Option D2 LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 0.781
2 | Access Road Construction |  |  |  | 1.109
3 | Cover over Tailings Pile Base |  |  |  | 2.557
4 | Channel Stabilization |  |  |  | 0.936
5 | Water Management |  |  |  | 0.145
6 | Support Equipment |  |  |  | 0.31
7 | Support Labour |  |  |  | 0.675
8 | Asbestos Control |  |  |  | 0.843
9 | Fuel Transportation |  |  |  | 0.022
10 | Indirects |  |  |  | 5.106
Note: Cost Breakdown in Appendix 3, Option WC-D2
Subtotal |  |  |  |  | 12.484
| EPCM |  |  |  | 1.2484
| Contingency (25%) |  |  |  | 3.4331
Total Estimated Capital Costs |  |  |  |  | 17.1655
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 0.065363
2.1 | Clear Vegetation from Existing Rock-Lined Channel | 20000 | 10 | 100 | 0.065363
3 | Replacement |  |  |  | 0.31666
2.1 | Replace 200m of 0.1% Channel (North Lobe) (Cost Breakdown in Appendix 3) | 705000 | 45 | 100 | 0.31666
2.2 | Replace 200m of 0.1% Channel (South Lobe) (Cost Breakdown in Appendix 3) | 705000 | 12 | 100 | 1.8711
Subtotal |  |  |  |  | 3.8872
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 3.8872
Equivalent Annual Operational Costs |  |  |  |  | 0.10617
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 21.0527
Maintaining Site Access |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Grade Access Road (15 km) | 40000 | 4 | 100 | 0.35269
2 | Site Access Road Resurfacing (16.2 km) (Cost Breakdown in Appendix 3) | 4318000 | 20 | 100 | 6.1891
3 | 15 m Long Bridge Replacement (Cost Breakdown in Appendix 3) | 1789000 | 50 | 100 | 0.67193
Subtotal |  |  |  |  | 7.2138
Total Estimated Cost (Over 100-Year Period) |  |  |  |  | 7.2138
Equivalent Annual Cost |  |  |  |  | 0.19702
Note: This is not considered a walk-away solution. Site access would need to be maintained in order to complete regular monitoring, maintenance and replacement.

## WC-E
|  | SHEET TITLE: |  | Wolverine Creek Option E LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 1.22
2 | Access Road Construction |  |  |  | 1.102
3 | Rock Drain |  |  |  | 6.935
4 | Tailings Stabilization |  |  |  | 4.8
5 | Cover over Tailings |  |  |  | 3.76
6 | Channel Stabilization |  |  |  | 1.024
7 | Water Management |  |  |  | 0.177
8 | Support Equipment |  |  |  | 0.79
9 | Support Labour |  |  |  | 2.834
10 | Asbestos Control |  |  |  | 0.79
11 | Fuel Transportation |  |  |  | 0.057
12 | Indirects |  |  |  | 12.367
Note: Cost Breakdown in Appendix 3, Option WC-E
Subtotal |  |  |  |  | 35.856
| EPCM |  |  |  | 3.5856
| Contingency (25%) |  |  |  | 9.8604
Total Estimated Capital Costs |  |  |  |  | 49.302
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 1.2452
2.1 | Excavate Rock Drain Sediment (at Inlet) (Cost Breakdown in Appendix 3) | 361000 | 10 | 100 | 1.1798
2.2 | Clear Vegetation from Existing Rock-Lined Channel | 20000 | 10 | 100 | 0.065363
Subtotal |  |  |  |  | 2.8792
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 2.8792
Equivalent Annual Operational Costs |  |  |  |  | 0.078637
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 52.1812
Note: While this is not entirely a walk-away solution, very little regular maintenance would be required for this option. Therefore site access would not need to be maintained.

## WC-E2
|  | SHEET TITLE: |  | Wolverine Creek Option E2 LCCA
|  | PROJECT NO. AND TITLE: |  | 307071-00895 Clinton Creek LCCA
|  | CLIENT: |  | Assessment and Abandoned Mines
|  | LOCATION: |  | Clinton Creek Site, YT
|  | ESTIMATE BASIS: |  | 2014 CDN Dollars (+/- 50% accuracy)
|  | DATE: |  | 2014-03-28
|  | REVISION: |  | 0
LIFECYCLE COST ANALYSIS
Capital Costs
Task No. | Description |  |  |  | Cost (2014 CAD)
1 | Mobilization |  |  |  | 1.22
2 | Access Road Construction |  |  |  | 1.102
3 | Tailings Stabilization |  |  |  | 5.6
5 | Cover over Tailings |  |  |  | 4.51
6 | Channel Stabilization |  |  |  | 1.024
7 | Water Management |  |  |  | 0.177
8 | Support Equipment |  |  |  | 0.66
9 | Support Labour |  |  |  | 1.89
10 | Asbestos Control |  |  |  | 0.79
11 | Fuel Transportation |  |  |  | 0.05
12 | Indirects |  |  |  | 8.45
Note: Cost Breakdown in Appendix 3, Option WC-E2
Subtotal |  |  |  |  | 25.473
| EPCM |  |  |  | 2.5473
| Contingency (25%) |  |  |  | 7.0051
Total Estimated Capital Costs |  |  |  |  | 35.0254
Operational Costs |  |  |  | 25% Contingency Incl., Real Discount Rate = | 2.5%
Task No. | Description | Cost (2014 CAD) | Frequency (Years) | Duration (Years) | NPC (2014 CAD)
1 | Monitoring |  |  |  | 1.6341
1.1 | Visual Inspections | 15000 | 1 | 100 | 0.54921
1.2 | Surveys | 60000 | 2 | 100 | 1.0849
2 | Maintenance |  |  |  | 0.03156
2.1 | Clear Vegetation from Existing Rock-Lined Channel | 20000 | 10 | 100 | 0.03156
Subtotal |  |  |  |  | 1.6656
Total Estimated Operational Costs (Over 100-Year Period) |  |  |  |  | 1.6656
Equivalent Annual Operational Costs |  |  |  |  | 0.045492
Total Estimated Lifecycle Costs (Over 100-Year Period) |  |  |  |  | 36.691
Note: This is considered a walk-away solution. Therefore site access would not need to be maintained.