## 1-1
Table 1-1. Summary of Completed Field Work and Data Evaluations Compared to Data Gaps Identified in the Revised Gaps Assessment Faro Mine Remediation Project Report (CH2M, March 2014o)
Faro Mine Remediation Project
Activity | Task | Surface Water Data Gap | Required Field Work | Summary of Completed Field Work and Data Evaluations
Site Wide
SW-005 | Surface Water Modelling | Site-specific physical data such as bed and bank materials within diversions. Subcatchment delineation in site specific model areas such as waste dumps. Conduct field surveys for use in surface water modelling; cross sections, floodplains, structures, and similar. Confirm locations and scope through field reconnaissance. This will be completed for individual activity locations. | Maintain existing flow monitors and rainfall monitors. Obtain additional meteorological data at existing stations if equipment operational. Obtain precipitation data concurrent with flow monitoring data collection. Collect continuous flow data at newly established monitoring locations. | Table 2-1 outlines the data collected in 2014 and 2015 for the surface water and seepage stations (31 and 8 stations respectively); both spot flow and continuous water level measurements. 38 of the 38 stations have staff gauges installed to record spot flow measurements. The following summarizes the spot flow data received for 2014 and 2015: - 20 stations with 2014 and 2015 - 5 stations with 2014 data only - 2 stations with 2015 data only - 11 stations with no 2014 or 2015 data 18 of the 38 stations have pressure transducers and level loggers installed to record continuous water level measurements. The following summarizes the continuous water level data received for 2014 and 2015: - 6 stations with 2014 and 2015 - 12 stations with no 2014 or 2015 data
Surface Water Diversions
102.1 | Faro Creek Diversion (East Valley) | Bed and bank materials characterizations. Additional flow monitoring data collection at recommended 2013 stations for additional model refinement. | Physical survey for cross sections, bed and bank materials characterizations, and floodplain cover. Monitor surface flow at North Fork Rose Creek monitoring stations and Faro Creek Diversion. | Ten cross section surveys were completed along the West Valley Interceptor Ditch on September 20 and September 22, 2014. Bed and bank material characterizations were completed during the field investigation conducted June 28 and June 29, 2014. North Fork Rose Creek monitoring stations include the following 11 stations: R7, R8, R9, R10, NF2, NFRC-SC1, NFRC-SC2, NFRC-SC3, NFRC-SC4, X2, and X3. Faro Creek Diversion monitoring stations include the following 7 stations: FDU (FCD-1), FCO, FCD-2, FCD-3, FCD-4, FCD, and FAROCR. Table 2-1 outlines the surface water monitoring data collected for these stations. A rapid geomorphic assessment was completed for the Faro Creek Diversion in 2014 and 2015 to assess the condition of the channel.
102.2 | Faro Creek Diversion (West Valley Interceptor Ditch) | Same as Activity 102.1. | Physical survey for cross sections, bed and bank materials characterizations, and floodplain cover. | Ten cross section surveys were completed along the West Valley Interceptor Ditch on September 20 and September 22, 2014. Channel cross section surveys were also completed in support of the North Faro Rose Creek Temporary Diversion design efforts. Bed and bank material characterizations were completed during the field investigation conducted June 28 and June 29, 2014. A rapid geomorphic assessment was completed for the West Valley Interceptor Ditch and the Faro Creek Diversion in 2014 and 2015 to assess the condition of the channel.
102.3 | North Wall Interceptor Ditch | Detailed cross section data including channel and floodplain for Upper Guardhouse Creek and the North Wall Interceptor Ditch for modelling obtained from LiDAR. Channel bed and bank materials characterizations for modelling. Assess area below Cross Valley Dam for discharge design requirements to Rose Creek – flow management and design requirements. | Surveys for detailed cross section data, bed and bank materials characterizations, and floodplain cover characterization. Collect ice data, flow data, and water profile data (surface water elevations). | Three channel cross section surveys were completed at Upper Guardhouse Creek and five at the North Wall Interceptor Ditch on September 18 and 21, 2014. Field reconnaissance of Upper Guardhouse Creek and the North Wall Interceptor Ditch was performed in 2014 and 2015 to assess their flood conveyance capacity, the condition of the channels, and their confluences. One surface water monitoring station, X5, is present in the West Perimeter Remediation Unit; spot flow data was collected from X5 in 2014 and 2015.
102.4 | Lower Guardhouse Creek | Detailed cross section data including channel and floodplain areas; channel and bed and bank materials characterizations; soils data including permafrost; historical channel ice data, flow monitoring, and water profile data (surface elevations). Additional flow monitoring data for model calibration and validation. | Surveys for detailed cross section data, bed and bank materials characterizations, and floodplain cover characterization. Evaluate flow data, and water profile data (surface elevations). Establish a flow monitoring station and collect continuous flow data. | No cross section surveys were conducted for Lower Guardhouse Creek. Field reconnaissance of Lower Guardhouse Creek was performed in 2014 and 2015 to assess the condition of the channel and its capacity for flood conveyance No flow monitoring station was established along Lower Guardhouse Creek.
203.1 | Rose Creek Diversion | Establish flow monitoring station on Rose Creek upstream from the confluence with the North Fork Rose Creek for model calibration and validation. Collect additional flow monitoring data at stations RCDC and X14. Determine existing channel morphology | Survey channel cross sections along the existing RCD upstream of the fuse plug. Conduct bed and bank material and floodplain cover characterization survey from the fuse plug to just downstream of the North Fork Rock Drain. | Two cross section surveys (cross sections RCD 43 and RCD 44) were completed at the Rose Creek Diversion on September 18, 2014. Stilling wells and water level transducers were installed at two existing staff gauge locations, RCSG-4 and X10. Four surface water monitoring stations (X3A, RCSG-4, X10, and X14) are present within the South Perimeter Remediation Unit. Spot flow data was collected at X3A, X10, and X14 in 2014 and 2015. No spot flow data was collected at RCSG-4 in either 2014 or 2015. Continuous water level data was collected for X14 in 2014 and 2015.
`

## 2-1
Table 2-1. Summary of Spot Flow and Continuous Flow Data Received for 2014 and 2015
Faro Mine Remediation Project
|  | Station Details |  | Available 2014 and 2015 Data
Reclamation Unit | Station Name | Type of Flow | Type of Station | Spot Flow | Continuous Water Level
West Perimeter | X5 | surface water | continuous water level | 2014, 2015 | None
East Perimeter | FDU (FCD-1) | surface water | continuous water level | 2014, 2015 | 2014, 2015 | Spot Flow
East Perimeter | FCD-2 | surface water | continuous water level | None | None | # of Stns capable of spot flow measurements: 39
East Perimeter | FCD-3 | surface water | continuous water level | 2015 | None | # Stns with 2014 and 2015 data: 20
East Perimeter | FCD-4 | surface water | continuous water level | 2015 | None | # Stns with 2014 data only: 5
East Perimeter | FCD | surface water | spot flow | None | N/A | # Stns with 2015 data only: 2
East Perimeter | FAROCR | surface water | spot flow | 2014, 2015 | N/A
East Perimeter | R7 | surface water | continuous water level | 2014, 2015 | 2014, 2015
East Perimeter | R8 | surface water | spot flow | None | N/A | Continuous Water Level
East Perimeter | R9 | surface water | spot flow | None | N/A | # of Stns capable of spot flow measurements: 18
East Perimeter | R10 | surface water | continuous water level | 2014, 2015 | None | # Stns with 2014 and 2015 data: 6
East Perimeter | NF2 | surface water | continuous water level | 2014, 2015 | 2014, 2015 | # Stns with 2014 data only: 0
East Perimeter | NFRC-SC1 | surface water | spot flow | None | N/A | # Stns with 2015 data only: 0
East Perimeter | NFRC-SC2 | surface water | spot flow | None | N/A
East Perimeter | NFRC-SC3 | surface water | spot flow | None | N/A
East Perimeter | NFRC-SC4 | surface water | spot flow | None | N/A
East Perimeter | X2 | surface water | continuous water level | 2014, 2015 | 2014, 2015
East Perimeter | R1 | surface water | continuous water level | 2014, 2015 | 2014, 2015
East Perimeter | X3 | surface water | spot flow | 2014, 2015 | N/A
South Perimeter | X3A | surface water | spot flow | 2014, 2015 | N/A
South Perimeter | RCSG-4 | surface water | continuous water level | None | None
South Perimeter | X10 | surface water | continuous water level | 2014, 2015 | None
South Perimeter | X14 | surface water | continuous water level | 2014, 2015 | 2014, 2015
Faro Pit | X22b | surface water | continuous water level | 2014, 2015 | None
Faro Pit | A-30 | seepage | spot flow | None | N/A
Waste Rock Dumps | FCO | surface water | spot flow | None | N/A
Waste Rock Dumps | SP5-6 | seepage | spot flow | 2014, 2015 | N/A
Mill Buildings Area and ETA | X7 | surface water | spot flow | 2014, 2015 | N/A
Mill Buildings Area and ETA | FCS-4 | surface water | continuous water level | 2014, 2015 | None
Mill Buildings Area and ETA | ETA Combined | surface water | continuous water level | 2014, 2015 | None
Mill Buildings Area and ETA | X23 | seepage | continuous water level | 2014 | None
Rose Creek Tailings Area | GDHSECK | surface water | spot flow | 2014, 2015 | N/A
Rose Creek Tailings Area | X4 | surface water | continuous water level | 2014, 2015 | None
Cross Valley Dam and Intermediate Dam and Associated Ponds | X5P | surface water | spot flow | 2014, 2015 | N/A
Cross Valley Dam and Intermediate Dam and Associated Ponds | Weir 3 | seepage | spot flow | 2014 | N/A
Cross Valley Dam and Intermediate Dam and Associated Ponds | X11 | seepage | spot flow | 2014 | N/A
Cross Valley Dam and Intermediate Dam and Associated Ponds | X12 | seepage | spot flow | 2014 | N/A
Cross Valley Dam and Intermediate Dam and Associated Ponds | X13 | seepage | spot flow | 2014 | N/A
Notes:
ETA = Emergency Tailings Area
N/A = not applicable