## Changes Req'd To 60% estimate
1 | Reduce volume of mill NAG in Activity 335 from 79,800 cm to 17,200 cm
2 | Increase volume of mill PAG in Activity 350 from 12,120 cm to 21,175 cm
3 | For NW Pile PAG, change comment in design report table 4.14 to say rock used in pit for 2m layers and not sent to TSF for mixing with tails
4 | Change Activity 220 to read "West Lower Pile - NAG rock" in both the P3 schedule and Excel estimate. Won't happen that way though.
5 | Change Activity 335 to add "SW Upper Pile" in the P3 schedule. In the Excel estimate, need to add SW Upper pile as a source. Quantities change from 79800/57450/0 to 17200/57450/50144 m3
6 | Remove reference to crushing the NAG rock before transporting to TSF for protection of exposed surfaces
7 | Change comment in Table 4.14 for West Mid Pile PAG to say "About 75% of this rock brought to TSF for mixing. Balance of rock brought straight to pit.
8 | On drawings, show pit fill levels after Seasons #2 and #3
9 | On drawings, show waste dump configurations at closure after the rock volumes in the estimate & schedule have been removed

## Unsorted Base Data
Activity ID | Borrow Source | Destination | Purpose | Bank Volume (bcm) | Swell Factor | Loose Volume (lcm) | Compaction Factor | Compacted Volume (ccm) | Item
215 | South Pile - NAG rock | Open Pit | Rock platform | 38750 |  |  |  |  | 1
220 | West Lower Pile - NAG rock | Open Pit | Rock platform | 4550 |  |  |  |  | 2 | Crushed
225 | Ore at pit entrance ramp | Open Pit | Final storage under pit cover | 8000 |  |  |  |  | 3
225 | South Pile - NAG rock | Open Pit | Open Pit Buttress | 5000 |  |  |  |  | 4
235 | SW Lower Pile - PAG rock | TSF | Equip traffic & mixing w/ tails | 46500 |  |  |  |  | 5
250 | Rock portion of tails/rock/subexc/toeberm mix | Open Pit | Final storage under pit cover | 27750 |  |  |  |  | 6 | Items 6 + 11 = 50% of Items 7 +12 +13
250 | Tails portion of tails/rock/subexc/toeberm mix | Open Pit | Final storage under pit cover | 55500 |  |  |  |  | 7 | Items 7 + 13 = 237,100 m3
255 | West Mid Pile - PAG rock | TSF | Equip traffic & mixing w/ tails | 29000 |  |  |  |  | 8
260 | NW Pile - PAG rock | Open Pit | Final storage under pit cover | 40800 |  |  |  |  | 9
320 | West Mid Pile - PAG rock | TSF | Equip traffic & mixing w/ tails | 68050 |  |  |  |  | 10
325 | Rock portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 115800 |  |  |  |  | 11 | Items 6 + 11 = 50% of Items 7 +12 +13
325 | Subexc portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 50000 |  |  |  |  | 12
325 | Tails portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 181600 |  |  |  |  | 13 | Items 7 + 13 = 237,100 m3
325 | Toe.berm portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 5800 |  |  |  |  | 14
330 | Sand from Main Dam and Seepage Dam | TSF Footprint | Protection of exposed TSF surfaces | 34325 |  |  |  |  | 15
335 | Mill Area - NAG rock | TSF Footprint | Protection of exposed TSF surfaces | 79800 |  |  |  |  | 16
335 | West Lower Pile - NAG rock | TSF Footprint | Protection of exposed TSF surfaces | 57450 |  |  |  |  | 17
335 | SW Upper Pile - NAG rock | TSF Footprint | Protection of exposed TSF surfaces | 0 |  |  |  |  | 18
345 | South Pile - NAG rock | Open Pit | Open Pit Buttress | 37850 |  |  |  |  | 19
345 | SW Upper Pile - NAG rock | Open Pit | Open Pit Buttress | 25350 |  |  |  |  | 20
350 | Concrete demolition waste | Open Pit | Final storage under pit cover | 2600 |  |  |  |  | 21
350 | Contaminated soils d/s of TSF seepage pond | Open Pit | Final storage under pit cover | 1000 |  |  |  |  | 22
350 | Hydrocarbon soils (Katza, mill, roads) | Open Pit | Final storage under pit cover | 9422 |  |  |  |  | 23
350 | Ketza shop PAG rock | Open Pit | Final storage under pit cover | 1787 |  |  |  |  | 24
350 | Mill Area - PAG rock | Open Pit | Final storage under pit cover | 12120 |  |  |  |  | 25
350 | Roads - PAG rock | Open Pit | Final storage under pit cover | 14777 |  |  |  |  | 26
350 | Subexc under seepage pond area | Open Pit | Final storage under pit cover | 600 |  |  |  |  | 27
350 | Tailings/soils from mill ponds | Open Pit | Final storage under pit cover | 2200 |  |  |  |  | 28
355 | East Pile - PAG rock | Open Pit | Final storage under pit cover | 20000 |  |  |  |  | 29
355 | NW Pile - PAG rock | Open Pit | Final storage under pit cover | 115617 |  |  |  |  | 30
355 | Ore stockpile | Open Pit | Final storage under pit cover | 1812 |  |  |  |  | 31
355 | West Mid Pile - PAG rock | Open Pit | Final storage under pit cover | 32851 |  |  |  |  | 32
375 | Victoria Creek Area sand | Open Pit | Interim cover | 80000 |  |  |  |  | 33
375 | West Lower Pile - NAG rock | Open Pit | Interim cover | 24000 |  |  |  |  | 34 | Crushed
415 | Sand from Main Dam and Seepage Dam | Stockpile Near Open Pit | To be used later for final cover | 69890 |  |  |  |  | 35

## Table 2.3.2-1 Recon Sum (hidden)
Table 2.3.2-1 Quantity Reconciliation Summary
Reconciliation Comments
Item | QUANTITY ITEM | AMEC (m3) | AECOM (m3) | Scope | Quantities | Pricing/Total Cost
1 | Tailings relocated to open pit | 237100 | 300000
2 | TSF subexc relocated to open pit | 50600 | 11000
3 | PAG rock first used for TSF mixing before transfer to open pit | 143550 | 0 | AMEC volume is 50% of items 1 and 2
4 | PAG rock relocated directly to pit | 237952 | 300000
5 | NAG rock relocated to pit for platform | 43300 | 44000
6 | NAG rock relocated to butttress | 68200 | 0
7 | NAG rock relocated to TSF for protection of exposed surfaces | 137250 | 0
8 | Miscellaneous other contaminated soils | 30834 | 0 | AECOM estimate covers some minor qtys with lump sums
9 | Dam material used for exposed TSF protection | 34325 | 32760
10 | Dam material returned to original borrow pits | 0 | 47240
11 | Dam material stockpiled for later use in final open pit cover | 69890 | 80000
12 | NAG rock for interim cover over open pit | 24000 | 0
13 | Victoria creek sand for interim cover over open pit | 80000 | 0
14 | Final cover over open pit | 72000 | 43000
Note: The color coding correlates to the quantity breakdown by schedule activity in Appendix ??

## Volumes by Schedule Activity
Schedule Activity ID | Borrow Source | Destination | Purpose | Bank Volume (bcm) | Item
215 | South Pile - NAG rock | Open Pit | Rock platform | 38750 | 1
220 | West Lower Pile - NAG rock | Open Pit | Rock platform | 4550 | 2 | Crushed
225 | Ore at pit entrance ramp | Open Pit | Final storage under pit cover | 8000 | 3
225 | South Pile - NAG rock | Open Pit | Open Pit Buttress | 5000 | 4
13000
235 | SW Lower Pile - PAG rock | TSF | Equip traffic & mixing w/ tails | 46500 | 5
250 | Rock portion of tails/rock/subexc/toeberm mix | Open Pit | Final storage under pit cover | 27750 | 6 | Items 6 + 11 = 50% of Items 7 +12 +13
250 | Tails portion of tails/rock/subexc/toeberm mix | Open Pit | Final storage under pit cover | 55500 | 7 | Items 7 + 13 = 237,100 m3
83250
255 | West Mid Pile - PAG rock | TSF | Equip traffic & mixing w/ tails | 29000 | 8
260 | NW Pile - PAG rock | Open Pit | Final storage under pit cover | 40800 | 9
320 | West Mid Pile - PAG rock | TSF | Equip traffic & mixing w/ tails | 68050 | 10
325 | Rock portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 115800 | 11 | Items 6 + 11 = 50% of Items 7 +12 +13
325 | Subexc portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 50000 | 12
325 | Tails portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 181600 | 13 | Items 7 + 13 = 237,100 m3
325 | Toe.berm portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 5800 | 14
353200
330 | Sand from Main Dam and Seepage Dam | TSF Footprint | Protection of exposed TSF surfaces | 34325 | 15
335 | Mill Area - NAG rock | TSF Footprint | Protection of exposed TSF surfaces | 79800 | 16
335 | West Lower Pile - NAG rock | TSF Footprint | Protection of exposed TSF surfaces | 57450 | 17
335 | SW Upper Pile - NAG rock | TSF Footprint | Protection of exposed TSF surfaces | 0 | 18
137250
345 | South Pile - NAG rock | Open Pit | Open Pit Buttress | 37850 | 19
345 | SW Upper Pile - NAG rock | Open Pit | Open Pit Buttress | 25350 | 20
63200
350 | Concrete demolition waste | Open Pit | Final storage under pit cover | 2600 | 21
350 | Contaminated soils d/s of TSF seepage pond | Open Pit | Final storage under pit cover | 1000 | 22
350 | Hydrocarbon soils (Katza, mill, roads) | Open Pit | Final storage under pit cover | 9422 | 23
350 | Ketza shop PAG rock | Open Pit | Final storage under pit cover | 1787 | 24
350 | Mill Area - PAG rock | Open Pit | Final storage under pit cover | 12120 | 25
350 | Roads - PAG rock | Open Pit | Final storage under pit cover | 14777 | 26
350 | Subexc under seepage pond area | Open Pit | Final storage under pit cover | 600 | 27
350 | Tailings/soils from mill ponds | Open Pit | Final storage under pit cover | 2200 | 28
44506
355 | East Pile - PAG rock | Open Pit | Final storage under pit cover | 20000 | 29
355 | NW Pile - PAG rock | Open Pit | Final storage under pit cover | 115617 | 30
355 | Ore stockpile | Open Pit | Final storage under pit cover | 1812 | 31
355 | West Mid Pile - PAG rock | Open Pit | Final storage under pit cover | 32851 | 32
170280
375 | Sand | Open Pit | Interim cover | 80000 | 33
375 | West Lower Pile - NAG rock | Open Pit | Interim cover | 24000 | 34 | Crushed
104000
415 | Sand from Main Dam and Seepage Dam | Stockpile Near Open Pit | To be used later for final cover | 69890 | 35
|  |  | Total NAG moved -----> | 272750
|  |  | Total PAG moved -----> | 381502 | (including 143,550 m3 first used at TSF for mixing, then rehandled)
|  |  | Total "Other Contaminated" moved -----> | 30834
|  |  | Tailings moved -----> | 237100
|  |  | Dam sand moved -----> | 104215
|  |  | Subexcavation moved -----> | 50600
|  |  | Sand moved -----> | 80000

## Volumes by End Purpose
Activity ID | Borrow Source | Destination | End Purpose | Bank Volume (bcm) | Item
215 | South Pile - NAG rock | Open Pit | Rock platform at bottom of pit | 38750 | 1
220 | West Lower Pile - NAG rock | Open Pit | Rock platform at bottom of pit | 4550 | 2 | Crushed
43300
250 | Tails portion of tails/rock/subexc/toeberm mix | Open Pit | Final storage under pit cover | 55500 | 7
325 | Tails portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 181600 | 13
325 | Subexc portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 50000 | 12
287100
250 | Rock portion of tails/rock/subexc/toeberm mix | Open Pit | Final storage under pit cover | 27750 | 6
325 | Rock portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 115800 | 11
|  |  |  | 143550 |  | Items 6 + 11 = 50% of Items 7 +12 +13
235 | SW Lower Pile - PAG rock | TSF | Equip traffic & mixing w/ tails | 46500 | 5
255 | West Mid Pile - PAG rock | TSF | Equip traffic & mixing w/ tails | 29000 | 8
320 | West Mid Pile - PAG rock | TSF | Equip traffic & mixing w/ tails | 68050 | 10
|  |  |  | 143550 |  | Matches above subtotal
225 | South Pile - NAG rock | Open Pit | Open Pit Buttress | 5000 | 4
345 | South Pile - NAG rock | Open Pit | Open Pit Buttress | 37850 | 19
345 | SW Upper Pile - NAG rock | Open Pit | Open Pit Buttress | 25350 | 20
68200
330 | Sand from Main Dam and Seepage Dam | TSF Footprint | Protection of exposed TSF surfaces | 34325 | 15
335 | Mill Area - NAG rock | TSF Footprint | Protection of exposed TSF surfaces | 79800 | 16 | Will be reduced to 17,200 m3 in 60% phase
335 | West Lower Pile - NAG rock | TSF Footprint | Protection of exposed TSF surfaces | 57450 | 17
335 | SW Upper Pile - NAG rock | TSF Footprint | Protection of exposed TSF surfaces | 0 | 18 | Will be increased to 50,400 m3 in 60% phase
171575
260 | NW Pile - PAG rock | Open Pit | Final storage under pit cover | 40800 | 9
350 | Ketza shop PAG rock | Open Pit | Final storage under pit cover | 1787 | 24
350 | Mill Area - PAG rock | Open Pit | Final storage under pit cover | 12120 | 25 | Will be increased to 21,175 m3 in 60% phase
350 | Roads - PAG rock | Open Pit | Final storage under pit cover | 14777 | 26
355 | East Pile - PAG rock | Open Pit | Final storage under pit cover | 20000 | 29
355 | NW Pile - PAG rock | Open Pit | Final storage under pit cover | 115617 | 30
355 | West Mid Pile - PAG rock | Open Pit | Final storage under pit cover | 32851 | 32
237952
225 | Ore at pit entrance ramp | Open Pit | Final storage under pit cover | 8000 | 3
325 | Toe.berm portion of tails/rock/subexc/toe.berm mix | Open Pit | Final storage under pit cover | 5800 | 14
350 | Concrete demolition waste | Open Pit | Final storage under pit cover | 2600 | 21
350 | Contaminated soils d/s of TSF seepage pond | Open Pit | Final storage under pit cover | 1000 | 22
350 | Hydrocarbon soils (Katza, mill, roads) | Open Pit | Final storage under pit cover | 9422 | 23
350 | Subexc under seepage pond area | Open Pit | Final storage under pit cover | 600 | 27
350 | Tailings/soils from mill ponds | Open Pit | Final storage under pit cover | 2200 | 28
355 | Ore stockpile | Open Pit | Final storage under pit cover | 1812 | 31
31434
375 | Sand | Open Pit | Interim cover | 80000 | 33
375 | West Lower Pile - NAG rock | Open Pit | Interim cover | 24000 | 34 | Crushed
104000
415 | Sand from Main Dam and Seepage Dam | Stockpile Near Open Pit | To be used later for final cover | 69890 | 35
69890